## Action log
Corrective Action Log
One line for every finding. Row 4 is an example: type over it. Days open and Overdue fill in by themselves.
No. | Date raised | Source | Location or area | Finding or hazard | Priority | Interim control | Corrective action | Control type | Assigned to | Due date | Status | Date completed | Verified by | Date verified | Effective? | Days open | Overdue? | Notes
CA-001 | 2026-09-23 | Inspection | North loading dock | Example: extension cord with damaged insulation in use | B | Cord tagged out and removed from service | Replace the cord and add cords to the weekly tool inspection | Administrative | Shop supervisor | 2026-10-07 | In progress |  |  |  |  | 10 | No | Example row: type over it.
Formulas:
Days open = IF([Date raised]="","",IF([Date completed]<>"",[Date completed]-[Date raised],TODAY()-[Date raised]))
Overdue? = IF(OR([Due date]="",[Date completed]<>"",[Status]="Cancelled"),"",IF([Due date]<TODAY(),"Yes","No"))

## Summary
Summary
Counts update as the Action log is filled in.
Status | Actions | Open by priority | Actions
Open | 0 | A Serious | 0
In progress | 1 | B Moderate | 1
Completed | 0 | C Minor | 0
Verified | 0
Cancelled | 0
Overdue | 0
Total logged | 1

## How to use
Corrective Action Log
General template. Adapt it to your work, your company procedures and the legal requirements that apply where you work.
How to use this template
1. Log every finding that needs action, whatever its source, on the Action log sheet. Give each one a number.
2. Set the priority, record what was done right away to make it safe, then the lasting corrective action.
3. Name one person and one due date for each action. Prefer controls higher in the order shown below.
4. When the work is done, enter the completion date. Someone else then checks that it worked and records the verification.
5. Review open and overdue actions at safety meetings. The Summary sheet shows the counts.
Cells shaded pale yellow are the ones to fill in. Everything else is the form itself: edit the wording to suit your work.
Priority
A Serious | Could cause death, permanent injury or major loss. Stop the work or correct right away.
B Moderate | Could cause a serious injury or illness. Correct promptly and control it in the meantime.
C Minor | Could cause a minor injury or damage. Correct on a set schedule.
Choose controls in this order
1. Eliminate | Remove the hazard or do the work a different way.
2. Substitute | Use a less hazardous material, tool or method.
3. Engineering | Guard, isolate, ventilate or barricade the hazard.
4. Administrative | Procedures, permits, training, signage, scheduling, spotters.
5. PPE | Protective equipment. The last line of defence, never the only one.
Days open and Overdue
Days open counts from Date raised to Date completed, or to today while the action is still open. Overdue shows Yes when the Due date has passed and there is no Date completed.